## BOM & Procurement
Item | Qty | Vendor | Unit Price (NPR) | Line Total (NPR) | Funding Source | Status | Action Ref | Notes
Wearable Node
ESP32-S3 (WROOM-1-CAM variant) | 2 | RoboNepal | 1979 | 3958 | 1 self-funded (Aaradhya) + 1 dept ask | Ordering pending — Action #16 spare unit not yet added | #16, #18, #19 | Add 1 spare unit at same order (bundle #16/#18/#19)
MPU6050 IMU | 1 | Lab-borrowed (KEC) | 0 | 0 | Lab-borrowed, no cost | Receipt/availability unconfirmed | #18 | Confirm in-hand and ready for integration testing
Lithium battery | 1 | TBD (sourcing) | 0 | 0 | Unpriced placeholder | Spec locked v28 (1000 mAh Li-ion/LiPo) — sourcing not started | — | 1000 mAh Li-ion/LiPo, locked v28 per R-05 endurance assumption (~8-10hr @ 5mA/200Hz)
USB-C cable | 1 | Self-funded | 0 | 0 | Self-funded (Aaradhya), price unlogged | Open — price not recorded | #19 | Log actual price once purchased
Charge/protection circuit (TP4056-class) | 1 | TBD (vendor, baseline SLT Pvt.Ltd) | 90 | 90 | Unpriced-baseline (legacy proposal pricing) | New v28 — required unless sourced battery is a protected pack | #32 | Added v28. Drop this line if the purchased battery cell already includes protection.
Enclosure (3D-printed PLA) | 1 | KEC Makerspace (in-house) | 0 | 0 | Material cost negligible; labor in-house | Method + form factor both resolved — wrist-worn (Action #8, locked v28) | #8, #11, #34 | Wrist-worn, locked v28. Electronics top-of-wrist/dorsal, locked v29 (Action #34). Threshold calibration (Action #7) can proceed against fixed geometry.
Compression arm sleeve (base layer, thumb-hole) | 1 | Daraz (Blue Bell / No Brand) | 136 | 136 | Self-funded (Aaradhya) — Daraz Rs.136 (was Rs.200, -32%) + Rs.100 std delivery | New v30 — enclosure base layer, closure mechanism locked (Velcro) | #34 | Worn under wrist enclosure per Action #34 (top-of-wrist placement + Velcro closure, v30). Product: BLUE BELL Let's Slim arm sleeve, thumb-hole, stretchable, light blue. Delivery to Kathmandu ~10-11 Aug.
Gateway
Acer Swift Go 16 (laptop, already owned) | 1 | Owned | 0 | 0 | No cost | Resolved — in hand | #15 | Compute sufficiency confirmed vs RPi 4B (v15)
Miscellaneous
BLE dongle | 1 | TBD (vendor) | 0 | 0 | Unpriced | Modality locked v28 — dongle required (phone app confirmed) | — | Phone app confirmed v28; dongle required over built-in BLE. Vendor/price not yet sourced.
Bring-up/Assembly
Breadboard + jumper wires | 2 | TBD (vendor, baseline SLT Pvt.Ltd) | 325 | 650 | Unpriced-baseline (legacy proposal pricing) | New v28 — bring-up/prototyping hardware | #33 | Added v28. 2 sets, per legacy table pricing (NPR 325/set).
Resistor/capacitor assortment | 1 | TBD (vendor, baseline Himalayan Solutions) | 600 | 600 | Unpriced-baseline (legacy proposal pricing) | New v28 — bring-up/prototyping hardware | #33 | Added v28. 1 lot, per legacy table pricing (NPR 600/lot).
TOTAL PROJECT COST |  |  |  | 5434
Source: dev_logs/SPARK_TRACKER.md §2.6, §1 (Actions #16,#18,#19,#32,#33,#34). Prior confirmed total ~NPR 15,004 (v22/v13); v28 added ~NPR 1,340 (Actions #32/#33); v30 adds NPR 136 arm sleeve (Action #34).