## BOM & Procurement
Item | Qty | Vendor | Unit Price (NPR) | Line Total (NPR) | Funding Source | Status | Action Ref | Notes
Wearable Node
ESP32-S3 (WROOM-1-CAM variant) | 2 | RoboNepal | 1979 | 3958 | 1 self-funded (Aaradhya) + 1 dept ask | Ordering pending — Action #16 spare unit not yet added | #16, #18, #19 | Add 1 spare unit at same order (bundle #16/#18/#19)
MPU6050 IMU | 1 | Lab-borrowed (KEC) | 0 | 0 | Lab-borrowed, no cost | Receipt/availability unconfirmed | #18 | Confirm in-hand and ready for integration testing
Lithium battery | 1 | TBD | 0 | 0 | Unpriced placeholder | Sourcing not started | — | Not yet specified (capacity/form factor TBD)
USB-C cable | 1 | Self-funded | 0 | 0 | Self-funded (Aaradhya), price unlogged | Open — price not recorded | #19 | Log actual price once purchased
Enclosure (3D-printed PLA) | 1 | KEC Makerspace (in-house) | 0 | 0 | Material cost negligible; labor in-house | Method resolved; form factor TBD | #8, #11 | Form factor depends on WP1.0/2.0 fall-sim results
Gateway
Acer Swift Go 16 (laptop, already owned) | 1 | Owned | 0 | 0 | No cost | Resolved — in hand | #15 | Compute sufficiency confirmed vs RPi 4B (v15)
Miscellaneous
BLE dongle / built-in BLE | 1 | TBD (phone app dependent) | 0 | 0 | Unpriced | Modality decision pending | — | Depends on gateway interface design (phone app vs laptop-only)
TOTAL PROJECT COST |  |  |  | 3958
Source: dev_logs/SPARK_TRACKER.md §2.6, §1 (Actions #16,#18,#19). Prior confirmed total ~NPR 15,004 (v22/v13).